## Table 1
Task Name | Duration | Start | Finish | Status
Sprint#1: Requirement Gathering | 15d | 2023-08-21 | 2023-09-05 | Completed
Define objective, scope | 5d | 2023-08-21 | 2023-08-25 | Completed
Learning about technology | 10d | 2023-08-26 | 2023-09-05 | Completed
Sprint#2: Project Structure | 16d | 2023-09-06 | 2023-09-21 | Completed
Database Management | 8d | 2023-09-06 | 2023-09-13 | Completed
Define Module | 8d | 2023-09-14 | 2023-09-21 | Completed
Sprint#3: Developing module | 16d | 2023-09-22 | 2023-09-14 | Completed
Developing model | 8d | 2023-09-22 | 2023-09-29 | Completed
Testing model | 8d | 2023-09-30 | 2023-10-07 | Completed
Sprint#4: Module Creation | 37d | 2023-10-08 | 2023-11-14 | Completed
UI Designing | 3d | 2023-10-08 | 2023-10-10 | Completed
User Authentication | 3d | 2023-10-11 | 2023-10-14 | Completed
Information Gathering | 4d | 2023-10-15 | 2023-10-18 | Completed
Post Project | 5d | 2023-10-19 | 2023-10-23 | Completed
Review Project | 5d | 2023-10-24 | 2023-10-28 | Completed
Forget Password | 5d | 2023-10-29 | 2023-11-02 | Completed
Upload CSV/DOWNLOAD CSV | 6d | 2023-11-03 | 2023-11-08 | Completed
File Download | 6d | 2023-11-09 | 2023-11-14 | Completed